## Project Schedule
1-YEAR PROJECT SCHEDULE GANTT CHART | [7 empty] | https://bit.ly/37lPrll
AT RISK | TASK NAME | SUB TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS | STATUS
| Task 1 - Preparation of thesis proposal |  | In Progress | Darllaine R. Lincopinis | 2023-04-24 | 2023-07-24 | 92 |  | Not Started
| Subtask 1.1 | Write a supporting paper of thesis concept | Complete | Darllaine R. Lincopinis | 2023-04-24 | 2023-06-08 | 46
| Subtask 1.2 | Write thesis proposal paper and PPT | In Progress | Darllaine R. Lincopinis | 2023-04-24 | 2023-07-24 | 92 |  | In Progress
| Task 2 - Presentation of thesis proposal |  | Not Started | Darllaine R. Lincopinis | 2023-07-26 | 2023-07-30 | 5 |  | Complete
| Subtask 2.1 | Preparation & Submission of thesis application to ethics committee | Not Started | Darllaine R. Lincopinis | 2023-07-26 | 2023-07-30 | 5 |  | On Hold
| Task 3 - Planning |  | Not Started | Darllaine R. Lincopinis | 2023-08-02 | 2023-09-05 | 35 |  | Overdue
| Task 4 - Data collection |  | Not Started | Darllaine R. Lincopinis | 2023-09-06 | 2023-10-06 | 31 |  | Needs Review
| Task 5 - Design |  | Not Started | Darllaine R. Lincopinis | 2023-10-08 | 2023-11-18 | 42 |  | Canceled
| Task 6 - Implementation and System prototyping |  | Not Started | Darllaine R. Lincopinis | 2023-11-19 | 2024-03-10 | 113
| Task 7 - Testing |  | Not Started | Darllaine R. Lincopinis | 2023-11-19 | 2024-03-10 | 113
| Task 8 - Submission of thesis |  | Not Started | Darllaine R. Lincopinis | 2024-04-02 | 2024-04-05 | 4
| Task 9 - Presentation of thesis |  | Not Started | Darllaine R. Lincopinis | 2024-04-02 | 2024-04-05 | 4
| Task 10 |  | Not Started |  | 2024-08-01 | 2024-08-10 | 10
| Task 11 |  | Not Started |  | 2024-08-11 | 2024-08-20 | 10
| Task 12 |  | Not Started |  | 2024-08-21 | 2024-08-30 | 10
| Task 13 |  | Not Started |  | 2024-09-01 | 2024-10-07 | 37
| Task 14 |  | Not Started |  | 2024-09-22 | 2024-11-22 | 62
| Task 15 |  | Not Started |  | 2024-10-17 | 2024-10-27 | 11
| Task 16 |  | Not Started |  | 2024-11-01 | 2024-12-31 | 61
| Task 17 |  | Not Started |  | 2024-12-22 | 2024-12-31 | 10
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Project Schedule
1-YEAR PROJECT SCHEDULE GANTT CHART TEMPLATE
AT RISK | TASK NAME | SUB TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS | STATUS
Not Started
In Progress
Complete
On Hold
Overdue
Needs Review
Canceled

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.